NOMIC Ramp  ·  Template  ·  nomicramp.com

Template

# Set-up checklist

For the person setting up the programme: the trust and the sampling plan the whole cycle depends on. Most programmes take 4 to 8 weeks from approval to the first observation.

## 1. Agree to do it

- ☐ Management sponsor named, and the business case approved

- ☐ Workforce representatives (and unions, where there are any) involved from the start

- ☐ Agreement on non-jeopardy and data use signed by both sides

- ☐ Data protection assessment completed with your data protection officer

- ☐ Decision on whether results will be shared with NOMIC (optional, de-identified)

## 2. Roles

- Programme lead: runs the cycle, keeps the backups, writes up results

- Observers: 4 or 5 experienced ground personnel for a first cycle (3 to 6 works), trusted by their peers

- Checking group: 2 or 3 of the observers, meeting regularly to check coding

- Learning Team host: someone who can run a session with planners and ramp staff

## 3. Plan the sample

- ☐ Number of turnarounds: about 75 to 100 for a first cycle (work it out with the sampling calculator)

- ☐ Spread across shifts (early, day, late, night), days of the week, aircraft types and stands

- ☐ Ports included, and roughly how many at each

- ☐ Busy and quiet times both covered

- ☐ Dates for the cycle, and for the checking sessions

## 4. Get ready

- ☐ Airport and company rules on mobile devices airside checked; permission obtained

- ☐ Observers trained and their practice coding checked

- ☐ Dictation tested in real ramp noise

- ☐ Observers' initials set in the tool, local codes added if needed

- ☐ A secure shared place for backup files, open only to the programme team

- ☐ Crew briefing sent out before the cycle starts

## 5. During and after the cycle

- ☐ Backups saved at least weekly and combined by the programme lead

- ☐ All observations checked before results are read

- ☐ Results shared with the workforce first

- ☐ One or two Learning Team sessions held, actions agreed

- ☐ Date set for the next cycle

NOMIC Ramp · nomicramp.com · hello@nomicramp.com. Adapt freely for your own organisation.